## Sheet1
BALU TASK LIST
SNO | DATE | TASK | PREFERENCE | STATUS
1 | 13/4/2017 | 1. DESIGN OF TABLES | IMP | DONE
|  | 2. DESIGN OF L-ANGLES FOR LIGHTS | IMP | NOT DONE
|  | 3. DESIGN OF CYNERGY SETUP | IMP | DONE
2 | 14/04/2017 | 1. SENDING ARM COVER FOR PRINTING | V.IMP | DONE
|  | 2. MODIFING L-ANGLE FOR LIGHTS | IMP | DONE
|  | 3. MODIFING THE CYNERGY SETUP | IMP | DONE
3 | 15/04/2017 | 1. DRILLING HOLES FOR U ANGLES | V.IMP | NOT DONE
|  | 2. SETUP THE TRACK FOR REAR WHEEL | V.IMP | NOT DONE
|  | 3. RE-ARRANGE THE ARM PERFECTLY | V.IMP | NOT DONE
|  | 4. RE-DESIGN OF CYKUL LOCK | V.IMP | NOT DONE
4 | 2017-04-17 | 1. DESIGN OF SOUTHCO LOCK MECHANISM | IMP | NOT DONE
5 | 2017-04-18 | 1. DESIGN OF HAND LOCK | IMP | NOT DONE
|  | 2. DESIGN OF CYCLES HANGING | IMP | NOT DONE
|  | 3. DESIGN OF LOCK CASE WITH NEW LOCK SYSTEM | IMP | NOT DONE
6 | 2017-04-19 | 1. DESIGN OF LOCK CASE WITH NEW LOCK SYSTEM | IMP | NOT DONE
|  | 2. DESIGN OF HAND LOCK | IMP | NOT DONE
|  | 3. C4 PPT | IMP | NOT DONE
|  | 4. DESIGN OF CONTAINER | IMP | NOT DONE
PUJA AND PRAVANYA
SNO | DATE | TASK | PREFERENCE | STATUS
1 | 13/4/2017 | 1. FORMATION OF SOCKET BETWEEN RASPBERRY PI AND ANDROID PHONE AND RFCOMM DESCRIPTION. | IMP | NOT DONE
|  | 2. DETAILS ABOUT SENDING DATA THROUGH PHONE AND ACCEPTING IT. | IMP | NOT DONE
|  | 3. RECEPTION OF DATA THROUGH CHANNEL AND ACCEPTING AND DECODING BYTES. | IMP | NOT DONE
2 | 14/04/2017 | 1. FORMATION OF SOCKET BETWEEN RASPBERRY PI AND ANDROID PHONE AND RFCOMM DESCRIPTION. | IMP | DONE
|  | 2. DETAILS ABOUT SENDING DATA THROUGH PHONE AND ACCEPTING IT. | IMP | DONE
|  | 3. RECEPTION OF DATA THROUGH CHANNEL AND ACCEPTING AND DECODING BYTES. | IMP | DONE
3 | 15/04/2017 | 1. BLUETOOTH CODE LINKED TO THE LOCK MECHANISM CODE | IMP | DONE
4 | 2017-04-17 | 1. SOKET CONNECTION TO WORK WITH DIFFERENT CHANNELS THROUGH APP | IMP | NOT DONE
5 | 2017-04-18 | 1. TRIED HAND-LOCK MECHANISM | IMP | DONE
|  | 2. BLUETOOTH USE-CASES | IMP | DONE
|  | 3. SOKET CONNECTION TO WORK WITH DIFFERENT CHANNELS THROUGH APP | IMP | DONE
6 | 2017-04-19 | 1. INSTALLED GIT HUB AND CREATED AN ACCOUNT IN GITHUB | IMP | DONE
|  | 2. C4 PPT | IMP | NOT DONE
|  | 3. CYCLE HAND LOCK | IMP | NOT DONE